## Slide 1: CPSC 3720: Lecture 3: Software Planning & Process
Eileen T. Kraemer and Murali Sitaraman, Clemson
E-mails: etkraem@clemson.edu and murali@Clemson.edu
Spring 2018 version
Some of the lecture slides have benefitted from the findings of grants from the US National Science Foundation.
Notes: Allow 15 minutes for lifecycle quiz

## Slide 2: Software Lifecycle Phases
Requirements analysis
Design and specification
Implementation
Quality Assurance
Maintenance

## Slide 3: Project Planning
Predictive planning
Adaptive planning

## Slide 4: Project Planning
Understand initial requirements and identify significant tasks
Remember the bottom line: High quality software on time on budget
Budget: Do cost estimates
Time: Set up project milestones

## Slide 5: Cost Estimation
Depends on prior project experiences and backgrounds of personnel
COCOMO (Constructive Cost Estimation Model)
Other cost estimation models

## Slide 6: COCOMO
developed by Barry W. Boehm in the late 1970s
  Software Engineering Economics (1981)
  Looked at codes with 2K to 100K LoC
  Assembly, PL/I
  Waterfall model

## Slide 7: COCOMO II
Also Boehm
Developed ‘95, published 2000
Includes agile development process*
Based on:
  more projects
  Desktop applications vs. mainframe/batch
  Reuse
  Off-the-shelf components
* In agile development processes solutions evolve through collaborative efforts of cross-functional teams.

## Slide 8: COCOMO
Three levels:
  Basic
    Good for quick/early/order of magnitude estimates
    Effort and cost as f(program_size)
    Program size expressed in SLOC, KLOC (source lines of code, thousands…)
  Intermediate
    Includes factors that account for differences in project attributes (cost drivers)
  Detailed
    Accounts for influence of project phase

## Slide 9: COCOMO
Deals with three kinds of projects
  Organic projects
    "small" teams with "good" experience working with "less than rigid" requirements
  Semi-detached projects
    "medium" teams with mixed experience working with a mix of rigid and less than rigid requirements
  Embedded projects
    developed within a set of "tight" constraints. It is also combination of organic and semi-detached projects.(hardware, software, operational, ...)

## Slide 10: COCOMO
  Effort Applied (E) = ab(KLOC)bb [ person-months]
  Development Time (D) = cb(Effort Applied)db [months]
  People required (P) = Effort Applied / Development Time [count]
Software project | ab | bb | cb | db
Organic | 2.4 | 1.05 | 2.5 | 0.38
Semi-detached | 3.0 | 1.12 | 2.5 | 0.35
Embedded | 3.6 | 1.20 | 2.5 | 0.32
Co-efficients from original analysis:

## Slide 11: Exercise – Basic COCOMO
You are asked to do cost estimation using basic COCOMO for a medium team with mixed experience working on a software development effort that will require 200,000 lines of code.
  What do you predict will be required for the effort applied?
  How long will the project take to develop?
  How many people are required?

## Slide 12: COCOMO - Intermediate
Includes “cost drivers”
Product attributes
  Required software reliability, Size of application database, Complexity of the product
Hardware attributes
  Run-time performance constraints, Memory constraints, Volatility of the virtual machine environment, Required turnabout time
Personnel attributes
  Analyst capability, Software engineering capability, Applications experience, Virtual machine experience, Programming language experience
Project attributes
  Use of software tools, Application of software engineering methods, Required development schedule

## Slide 13: COCOMO - Detailed
Uses different effort multipliers for each cost driver attribute depending on phase:
  Planning & requirements
  Systems design
  Detailed design
  Module code & test
  Integration & test
  …

## Slide 14: Other cost estimation approaches:
COSYMO
Evidence-based Scheduling
Function Point Analysis
Parametric Estimation
ITK
Putnam model
Others …

## Slide 15: Process Models
Linear
  Classical Waterfall Model
Iterative

## Slide 16: Classical Waterfall Model
Requirements Analysis
Design & Specification
Implementation
Quality Assurance
Maintenance

## Slide 17: Linear Process Models
Classical Waterfall model
  Advantages: Allows for predictive planning (reading)
  Disadvantages: No feedback
    Realistic software processes do not work in a linear fashion

## Slide 18: Iterative Process Models
Iterative process models (listed on the next slide)
  Advantages: Allow for adaptive planning (reading)
  Advantages: Feedback
  Disadvantages:
    Since things change, it is difficult to stick to plans
    But there is no real alternative

## Slide 19: Iterative Process Models
Spiral Process Model
Incremental Process Mode
Rational Unified Process (RUP) Model
Agile Models
Various others, including combinations of the above

## Slide 20: Spiral Process Model
Notes: In 1988, Barry Boehm published a formal software system development "spiral model," which combines some key aspect of the waterfall model and rapid prototyping methodologies, in an effort to combine advantages of top-down and bottom-up concepts. It provided emphasis in a key area many felt had been neglected by other methodologies: deliberate iterative risk analysis, particularly suited to large-scale complex systems.
The basic principles are:[1]
* Focus is on risk assessment and on minimizing project risk by breaking a project into smaller segments and providing more ease-of-change during the development process, as well as providing the opportunity to evaluate risks and weigh consideration of project continuation throughout the life cycle.
* "Each cycle involves a progression through the same sequence of steps, for each part of the product and for each of its levels of elaboration, from an overall concept-of-operation document down to the coding of each individual program."[9]
* Each trip around the spiral traverses four basic quadrants:
(1) determine objectives, alternatives, and constraints of the iteration;
(2) evaluate alternatives; Identify and resolve risks;
(3) develop and verify deliverables from the iteration; and
(4) plan the next iteration.[10]
Begin each cycle with an identification of stakeholders and their "win conditions", and end each cycle with review and commitment.[11]

## Slide 21: Iterative / Incremental Process Model
Notes: any combination of both iterative design or iterative method and incremental build model for software development.
The combination is of long standing[1] and has been widely suggested for large development efforts. For example, the 1985 DOD-STD-2167[2] mentions (in section 4.1.2): "During software development, more than one iteration of the software development cycle may be in progress at the same time." and "This process may be described as an 'evolutionary acquisition' or 'incremental build' approach.“
The relationship between iterations and increments is determined by the overall software development methodology and software development process.
The exact number and nature of the particular incremental builds and what is iterated will be specific to each individual development effort.
Iterative and incremental development are essential parts of the Modified waterfall models, Rational Unified Process, Extreme Programming and generally the various agile software development frameworks.
It follows a similar process to the plan-do-check-act cycle of business process improvement.

## Slide 22: Rational Unified Process Model
Unified Process –
  popular iterative/incremental software process framework
  Four phases:
    Inception
    Elaboration (milestone)
    Construction (release)
    Transition (final production release)
Rational Unified Process (RUP)
  A version of Unified Process created by the Rational Software Corp., a division of IBM
  an adaptable framework, intended to be tailored by the software project teams that select elements that are appropriate for their needs

## Slide 23: Rational Unified Process

## Slide 24: Agile Models
Cross-functional teams
Requirements & solutions evolve
Adaptive planning, evolutionary development, early delivery, continuous improvement
Manifesto:
  Individuals and Interactions more than processes and tools
  Working Software more than comprehensive documentation
  Customer Collaboration more than contract negotiation
  Responding to Change more than following a plan
Examples:
  Scrum
  Kanban

## Slide 25: Agile Models
Scrum:
  teams of 3-9 developers
  work in 1 to 4 week cycles (sprints)
  Check progress daily in 15 minute standup meetings
  Deliver workable software after every sprint
Kanban
  method for visualizing the flow of work
  Goal is to balance demand with capacity, spot bottlenecks
  Pull versus push

## Slide 26: Process Vs. Product Discussion
Notes: Allow at least 15 minutes. Student groups of 3 take a stand: Process is more important or Product is more important. Make sure there are enough groups for both sides. Have Process group call out their first key point. Product group then does two. Process group does two. Then Product group does one. Conclude noting that they are both important!

## Slide 27: Process Quality: CMM
CMM = Capability Maturity Model
  Watts Humphrey @ CMU’s SEI
    Managing the Software Process (1989)
Levels:
  Initial
  Repeatable
  Defined
  Managed
  Optimizing

## Slide 28: CMM Characterization of Ratings
Initial
  Ad hoc
Repeatable
  A repeatable process is in place
Defined
  Above + Standards are in place
Managed
  Above + Metrics collection is in place
Optimizing
  Above + Continuous improvement methods are in place

## Slide 29: Team Formation
Team projects are weighted heavily
Three members per team, no more, no less; If the number of students is not divisible by 3, it may be necessary to have one or two teams of 2 students
Talk to your friends and form teams by next week
If you don’t take the initiative, you may be assigned to a team randomly at the instructor’s discretion
Notes: Due before the next class